# Stephen — FY27 Work Plan

Objective One: Coded-Conversion and Excel-AI-CPAT (Mitigation and Distribution)

Goal Description: Build the Excel-AI-CPAT and the Coded-Conversion (Python), with one set of equations and one scope: basic mitigation (prices and energy use equations), power, remaining mitigation and distribution; and a Shiny app as the online dashboard (50 days). Components: • 1a: Excel-AI-CPAT: basic mitigation, power, remaining mitigation and distribution • 1b: Coded-Conversion (Python): the same scope • 1c: Shiny app (online dashboard) Not included: Other Mitigation (GDP, IMF-Transport-mitigation); GHG accounting and crediting (Objective Two); Co-benefits (Transport, Air Pollution); integration of mitigation code with air pollution code. Milestones: 1a_m1: Delivery of Excel-AI-CPAT mitigation MVP by 23 October 2026 1a_m2: Delivery of final Excel-AI-CPAT by 4 December 2026 1b_m1: Delivery of final Coded-Conversion (Python) by 11 December 2026 1c_m1: Delivery of final Shiny app by 5 February 2027 KPI/Metrics: Delivery of 4 key milestones (1a_m1, 1a_m2, 1b_m1, 1c_m1) Due Date : 2027/03/20

Objective Two: Applications of Coded-Conversion and Excel-AI-CPAT

Goal Description: Apply the Coded-Conversion and Excel-AI-CPAT, within what exists already, to GHG accounting, policy crediting, FFI, pathways and pilot country projects, and get existing models working smoothly (35 days). Components: • 2a: GHG accounting*, Policy crediting* and the Framework for Financial Incentives (FFI)*, including the Total Carbon Price • 2b: Existing models working smoothly: FTT and MFMod (tbc) • 2c: Pathways tool* and pilot country projects, with planning and Egypt work * Simple tool only: the AI-based Excel tool applied to these uses. Milestones: 2b_m1: Completion of Zoe's FTT project by 27 November 2026 2c_m1: Delivery of pathways tool (complete) by 15 January 2027 2b_m2: Delivery of existing models working smoothly: FTT and MFMod (tbc) by 12 February 2027 2a_m1: Delivery of the application to GHG accounting, crediting and FFI by 5 March 2027 KPI/Metrics: Delivery of 4 key milestones (2b_m1, 2c_m1, 2b_m2, 2a_m1) Due Date : 2027/03/20

Objective Three: Other Tools - Tax and Macro-Fiscal Dashboard, Excise Diagnostic and Energy GP cross-support

Goal Description: Hand over the Excise Diagnostic and the Tax and Macro-Fiscal Dashboard to the team at their current scope, with Energy GP cross-support (tbc) if funded (40 days: 25 spent, 15 remaining). Components: • 3a: Excise Diagnostic • 3b: Tax and Macro-Fiscal Dashboard • 3c: Energy GP cross-support (tbc) Milestones: 3a_m1: Delivery of Excise Diagnostic MVP by 25 September 2026 3b_m1: Delivery of Tax and Macro-Fiscal Dashboard MVP by 25 September 2026 3a_m2: Delivery of Excise Diagnostic to Dirk by 16 October 2026 3b_m2: Delivery of Tax and Macro-Fiscal Dashboard to Dirk by 23 October 2026 KPI/Metrics: Delivery of 4 key milestones (3a_m1, 3b_m1, 3a_m2, 3b_m2); 4 complete Due Date : 2027/03/20

MVP = Minimum Viable Product.

## Time and Funding

| Code | Objective / sub-objective | Days | Funding source |
| --- | --- | --- | --- |
| 1 | Objective One: Coded-Conversion and Excel-AI-CPAT (Mitigation and Distribution) | 50 | TF-CSF-LTS |
| 1a | Excel-AI-CPAT | 20 | TF-CSF-LTS |
| 1b | Coded-Conversion (Python) | 15 | TF-CSF-LTS |
| 1c | Shiny app (online dashboard) | 15 | TF-CSF-LTS |
| 2 | Objective Two: Applications of Coded-Conversion and Excel-AI-CPAT | 35 |  |
| 2a | Application to GHG accounting, crediting and FFI | 15 | TF-TCAF-Crediting |
| 2b | Existing models working smoothly: FTT and MFMod (tbc) | 5 | TF-CSF-LTS |
| 2c | Pathways integration and pilot country projects, with planning and Egypt work | 15 | TF-CSF-LTS |
| 3 | Objective Three: Other Tools - Tax and Macro-Fiscal Dashboard, Excise Diagnostic and Energy GP cross-support | 40 |  |
| 3a | Excise Diagnostic | 20 | TF-GTP-NONSECO |
| 3b | Tax and Macro-Fiscal Dashboard | 20 | TF-GTP-SECO |
|  | Total (funded) | 125 |  |
| 4 | Currently tbc/unfunded: e.g. Energy GP cross support | 16 | Unfunded |
|  | Grand total (incl. unfunded) | 141 |  |

## Funding Sources

| Code | Funding source / sub-component | Days | Charge code |
| --- | --- | --- | --- |
|  | TF-CSF-LTS | 70 | AA-P508228-GPLG-TF0C8701 |
| 1a | Excel-AI-CPAT | 20 |  |
| 1b | Coded-Conversion (Python) | 15 |  |
| 1c | Shiny app (online dashboard) | 15 |  |
| 2b | Existing models working smoothly: FTT and MFMod (tbc) | 5 |  |
| 2c | Pathways integration and pilot country projects, with planning and Egypt work | 15 |  |
|  | TF-TCAF-Crediting | 15 | To be confirmed |
| 2a | Application to GHG accounting, crediting and FFI | 15 |  |
|  | TF-GTP-NONSECO | 20 | AA-P508228-GPLG-TF0C9102 |
| 3a | Excise Diagnostic | 20 |  |
|  | TF-GTP-SECO | 20 | AA-P508228-GPLG-TF0C7596 |
| 3b | Tax and Macro-Fiscal Dashboard | 20 |  |
|  | Total (funded) | 125 |  |
|  | Currently tbc/unfunded: e.g. Energy GP cross support | 16 |  |
|  | Grand total (incl. unfunded) | 141 |  |

## Milestones and Sequencing

| Code | Task / milestone | Days | From | To | Status |
| --- | --- | --- | --- | --- | --- |
| - | Leave | 10 | 29 Jun 2026 | 10 Jul 2026 |  |
| 3a/3b | Excise Diagnostic and Tax and Macro-Fiscal Dashboard: proofs of concept | 10 | 13 Jul 2026 | 31 Jul 2026 | Complete |
| - | Leave without pay, used for personal research; no plan time drawn | 20 | 3 Aug 2026 | 28 Aug 2026 |  |
| 3a/3b | Excise Diagnostic and Tax and Macro-Fiscal Dashboard: MVPs built | 15 | 31 Aug 2026 | 25 Sep 2026 | Complete |
| 3a_m1 | Delivery of Excise Diagnostic MVP |  |  | 25 Sep 2026 | Complete |
| 3b_m1 | Delivery of Tax and Macro-Fiscal Dashboard MVP |  |  | 25 Sep 2026 | Complete |
| 2c | Planning and Egypt work | 5 | 28 Sep 2026 | 2 Oct 2026 | Complete |
| 1a | Excel-AI-CPAT MVP: basic mitigation (prices and energy use equations) | 5 | 5 Oct 2026 | 9 Oct 2026 | In progress |
| 1a_m1 | Delivery of Excel-AI-CPAT mitigation MVP |  |  | 23 Oct 2026 | Open |
| 3a | Excise Diagnostic: build handover pack | 5 | 12 Oct 2026 | 16 Oct 2026 | Complete |
| 3a_m2 | Delivery of Excise Diagnostic to Dirk |  |  | 16 Oct 2026 | Complete |
| 3b | Tax and Macro-Fiscal Dashboard: build handover pack | 5 | 19 Oct 2026 | 23 Oct 2026 | Complete |
| 3b_m2 | Delivery of Tax and Macro-Fiscal Dashboard to Dirk |  |  | 23 Oct 2026 | Complete |
| - | Vacation | 5 | 26 Oct 2026 | 30 Oct 2026 |  |
| 1a/1b | Power, in Excel-AI-CPAT and Python | 10 | 2 Nov 2026 | 13 Nov 2026 | Planned |
| 1a/1b | Remaining mitigation, in Excel-AI-CPAT and Python | 10 | 16 Nov 2026 | 27 Nov 2026 | Planned |
| 1a/1b | Distribution, in Excel-AI-CPAT and Python | 5 | 30 Nov 2026 | 4 Dec 2026 | Planned |
| 2b_m1 | Completion of Zoe's FTT project |  |  | 27 Nov 2026 | Open |
| 1a_m2 | Delivery of final Excel-AI-CPAT |  |  | 4 Dec 2026 | Open |
| 1b | Python code: testing and documentation | 5 | 7 Dec 2026 | 11 Dec 2026 | Planned |
| 1b_m1 | Delivery of final Coded-Conversion (Python) |  |  | 11 Dec 2026 | Open |
| - | Buffer (reserved; not for scheduling) | 5 | 15 Dec 2026 | 22 Dec 2026 |  |
| - | Christmas leave | 10 | 23 Dec 2026 | 1 Jan 2027 |  |
| 2c | Pathways tool integration (CPAT-SiSePuede) | 5 | 4 Jan 2027 | 8 Jan 2027 | Planned |
| 2c | Pilot country projects | 5 | 11 Jan 2027 | 15 Jan 2027 | Planned |
| 2c_m1 | Delivery of pathways tool (complete) |  |  | 15 Jan 2027 | Open |
| 1c | Shiny app: initial investigation and set-up | 5 | 18 Jan 2027 | 22 Jan 2027 | Planned |
| 1c | Shiny app: build, testing and documentation | 10 | 25 Jan 2027 | 5 Feb 2027 | Planned |
| 1c_m1 | Delivery of final Shiny app |  |  | 5 Feb 2027 | Open |
| 2b | Existing models: FTT and MFMod (tbc) on one Python platform | 5 | 8 Feb 2027 | 12 Feb 2027 | Planned |
| 2b_m2 | Delivery of existing models working smoothly: FTT and MFMod (tbc) |  |  | 12 Feb 2027 | Open |
| 2a | Excel-AI-CPAT with GHG accounting MVP, including the Total Carbon Price | 5 | 15 Feb 2027 | 19 Feb 2027 | Planned |
| 2a | Application to GHG accounting, crediting and FFI | 10 | 22 Feb 2027 | 5 Mar 2027 | Planned |
| 2a_m1 | Delivery of the application to GHG accounting, crediting and FFI |  |  | 5 Mar 2027 | Open |
| 3a/3b | Follow-up support to Dirk: Excise Diagnostic and Tax and Macro-Fiscal Dashboard | 5 | 8 Mar 2027 | 12 Mar 2027 | Planned |
| - | Final handover (the contract ends 20 March) |  | 15 Mar 2027 | 19 Mar 2027 | Planned |
| 3c | Energy GP cross-support (tbc) | 0 | Not slotted |  | Not funded |

# Project Information

## Objective One: Coded-Conversion and Excel-AI-CPAT (Mitigation and Distribution) (1a, 1b, 1c)

### Context

The update to the Climate Change Action Plan recommended corporate greenhouse gas accounting for Development Policy Financing. CPAT is the Bank’s established tool for the emissions effects of carbon pricing and fuel taxation, and the natural starting point. The IMF and the Bank are jointly developing a new user interface for Excel CPAT, but no work is currently planned to upgrade the back end, which remains in a large legacy Excel file — making it hard to adjust the calculation engine or have full transparency over the formulas. The CPAT engine can be more easily updated in AI-coded Python or AI-coded Excel form. This is consistent with the pathways work program with David Groves (Objective Two, 2c).

### Purpose

To produce, using AI, the Excel-AI-CPAT (1a, a cut-down version of CPAT in Excel) and the Coded-Conversion (1b, in Python), which share one set of equations, kept equal by script, and the same scope: basic mitigation (prices and energy use equations), power, remaining mitigation and distribution; and a Shiny app (1c) as the online dashboard for the coded version.

### Scope

In scope

- 1a Excel-AI-CPAT: from MVP (1a_m1, 23 October) to final version (1a_m2, 4 December).

- 1b Coded-Conversion (Python): the same scope, tested for delivery in December (1b_m1, 11 December).

- 1c Shiny app: initial investigation and set-up, then build and testing (1c_m1, 5 February).

- 1a/1b An agreed approach to integrating the new engine into the WB–IMF CPAT process.

Out of scope

- CPAT Excel validation, including of the legacy CPAT Excel file (see the separate CPAT Validation note).

- Other Mitigation (GDP, IMF-Transport-mitigation); GHG accounting and crediting (Objective Two); Co-benefits (Transport, Air Pollution); integration of mitigation code with air pollution code.

- Applications (Objective Two) and other tools (Objective Three).

### Product / Outcome

Product. An easy-to-use tool that calculates ex-ante estimates for fuel-pricing policies, in Excel (1a) and in Python (1b), with a Shiny app as its online dashboard (1c). A prototype already exists. For a given fuel-pricing policy, it gives the expected emissions effect, with the parameters and assumptions behind it visible; GHG accounting builds on it in Objective Two.

Outcome (to confirm). A transparent, updatable engine for the Bank, which may be the basis for the ex-ante GHG accounting that DPF operations require — operations that turn on policy reforms rather than physical assets, and for which no operational tool currently exists.

## Objective Two: Applications of Coded-Conversion and Excel-AI-CPAT (2a, 2b, 2c)

### Context

Applications of the Coded-Conversion and Excel-AI-CPAT, within what exists already, as simple tools only.

2a  GHG accounting for Development Policy Financing is a corporate requirement, led with the Outcomes unit, with the Total Carbon Price linked to its metric. Policy crediting and the FFI (cross-border climate externalities) could use the same machinery.

2c  A work program with David Groves is consolidating CPAT, CPM (formerly SiSePuede), MANAGE and MINDSET into one country policy analysis tool, first applied in Libya, Egypt and Morocco; its first phase ended in July 2026. Pilot country projects, starting with Egypt, apply the tools in country.

### Purpose

To apply the Coded-Conversion and Excel-AI-CPAT to GHG accounting, policy crediting and FFI (2a) and to the pathways tool and pilot country projects (2c); and to get the existing models (CPAT, MFMod-Python (tbc) and FTT) working smoothly together (2b).

### Scope

In scope

- 2a An Excel-AI-CPAT GHG accounting MVP, including the Total Carbon Price; then the application to GHG accounting, crediting and FFI (2a_m1, 5 March).

- 2b A common Python platform for CPAT, MFMod-Python (tbc) and FTT, with one user guide; FTT ready to run, with data aligned to CPAT countries (2b_m2, 12 February). Zoe's FTT project completes first (2b_m1, 27 November).

- 2c Planning and Egypt work (week of 28 September) and pilot country projects (week of 11 January).

- 2c Pathways tool integration (week of 4 January), with the tool complete by 15 January (2c_m1): supervising the CPM team integrating coded CPAT into SiSePuede (prices, policies, air pollution translation); the CPAT-LTS investment approach and policy interface; the Morocco application.

Out of scope

- Anything beyond the simple Excel-AI-CPAT tool for each use; building the engine itself (Objective One).

- Full integration of FTT and MFMod into CPAT, and further model development.

### Product / Outcome

2a  A simple Excel-AI-CPAT tool giving a GHG accounting figure for a fuel-pricing policy, including the Total Carbon Price; then applied to crediting and FFI. Outcome: a first tool for the ex-ante GHG accounting that DPF operations require.

2b  CPAT, MFMod-Python (tbc) and FTT on one platform, with a shared set-up and one user guide. Outcome: existing models that are easier to run together.

2c  A country policy analysis tool in which coded CPAT and SiSePuede share inputs and outputs, and pilot country applications. Outcome: consistent prices, policies and assumptions across the Bank’s country models.

## Objective Three: Other Tools - Tax and Macro-Fiscal Dashboard, Excise Diagnostic and Energy GP cross-support (3a, 3b, 3c)

### Context

Two AI-built MVPs were delivered on 25 September 2026 (3a_m1, 3b_m1), after five weeks of work in July and September. They are handed over to Dirk and the team as they stand.

3a  The Excise Diagnostic is a cross-country method for reviewing excise schedules and the wider country tax system (excises, subsidies and electricity pricing), set out in a working paper and process specification and applied to countries such as Liberia, Sierra Leone and Uganda.

3b  The Tax and Macro-Fiscal Dashboard shows 53 indicators for 217 countries (macro-fiscal, excise and other tax, and the Total Carbon Price), built with AI and with a full data audit trail.

3c  Energy GP cross-support (tbc) would be on a model that mixes the Treasury GP finance model with the Energy GP model, intended to find opportunities for concessional financing. It is not funded.

### Purpose

To hand the Excise Diagnostic (3a) and the Tax and Macro-Fiscal Dashboard (3b) to Dirk and the team at their current scope, ready to use and maintain without further development; and, only if funded, to give Energy GP cross-support (3c, tbc; 0–2 weeks).

### Scope

In scope

- 3a Build the Excise Diagnostic handover pack in the week of 12 October, with a user guide and example scripts; delivery to Dirk on 16 October (3a_m2). Complete: delivered to Dirk early, in the week of 5 October.

- 3b Build the Tax and Macro-Fiscal Dashboard handover pack in the week of 19 October, with a user guide and example scripts; delivery to Dirk on 23 October (3b_m2). Complete: delivered to Dirk early, in the week of 5 October.

- 3a/3b One week of follow-up support to Dirk, from 8 March.

- 3c Code help on the Treasury GP–Energy GP model, only if funded (tbc).

Out of scope

- Further development of either tool after handover, including new indicators or countries.

- Policy issue reports (dropped).

### Product / Outcome

3a  The Excise Diagnostic — a structured review of a country's excise schedules (fuel, vehicles, health-related and other) and related subsidies and electricity pricing — with its handover pack.

3b  The Tax and Macro-Fiscal Dashboard, with its handover pack.

3c  If funded (tbc): working code for parts of the Treasury GP–Energy GP model, to help find opportunities for concessional financing.

Outcome (to confirm). Country teams get quick, traceable tax and macro-fiscal diagnostics without new development, which can support policy dialogue on excises, subsidies and carbon pricing.

# Appendix: Task Breakdown and Further Detail

## Objective One: Coded-Conversion and Excel-AI-CPAT (Mitigation and Distribution) (1a, 1b, 1c)

### Tasks and Milestones

| Code | Task / milestone | Days | From | To | Status |
| --- | --- | --- | --- | --- | --- |
| 1a | Excel-AI-CPAT MVP: basic mitigation (prices and energy use equations) | 5 | 5 Oct 2026 | 9 Oct 2026 | In progress |
| 1a_m1 | Delivery of Excel-AI-CPAT mitigation MVP |  |  | 23 Oct 2026 | Open |
| 1a/1b | Power, in Excel-AI-CPAT and Python | 10 | 2 Nov 2026 | 13 Nov 2026 | Planned |
| 1a/1b | Remaining mitigation, in Excel-AI-CPAT and Python | 10 | 16 Nov 2026 | 27 Nov 2026 | Planned |
| 1a/1b | Distribution, in Excel-AI-CPAT and Python | 5 | 30 Nov 2026 | 4 Dec 2026 | Planned |
| 1a_m2 | Delivery of final Excel-AI-CPAT |  |  | 4 Dec 2026 | Open |
| 1b | Python code: testing and documentation | 5 | 7 Dec 2026 | 11 Dec 2026 | Planned |
| 1b_m1 | Delivery of final Coded-Conversion (Python) |  |  | 11 Dec 2026 | Open |
| 1c | Shiny app: initial investigation and set-up | 5 | 18 Jan 2027 | 22 Jan 2027 | Planned |
| 1c | Shiny app: build, testing and documentation | 10 | 25 Jan 2027 | 5 Feb 2027 | Planned |
| 1c_m1 | Delivery of final Shiny app |  |  | 5 Feb 2027 | Open |
|  | Total | 50 |  |  |  |

### Implementation

Every figure is traceable to an equation, a parameter and a source, so that the model can be updated regularly. The AI development work is front-loaded deliberately: building the coded core first means the methodology can be adjusted once discussions on it have run their course, rather than the sequence having to wait on methodological agreement.

1a  The Excel-AI-CPAT MVP (basic mitigation) in the week of 5 October, committed for delivery by 23 October (1a_m1).

1a/1b  Then, in Excel-AI-CPAT and Python together: power from 2 November (two weeks), remaining mitigation from 16 November (two weeks) and distribution in the week of 30 November. The Excel-AI-CPAT is delivered on 4 December.

1b  One week of Python testing and documentation from 7 December, for delivery on 11 December, before the Christmas leave.

1c  The Shiny app is investigated and set up in the week of 18 January, then built and tested, for delivery on 5 February.

### Uncertainties

Existing CPAT is not well validated and has not been published. It is not clear whether it is suitable for ex-post work, or for baseline analysis. The scope of policies to be included also needs to be settled.

### Requirements and Resources

- Requirements: CPAT coded / Excel-AI-CPAT proof of concept (WB–IMF process)

- CPAT Equations List; CPAT repo; CPAT Prices Database

- AI tools: GitHub Copilot (and Claude); personal mode for code, with proprietary data taken out; enterprise AI only for WB-confidential material

## Objective Two: Applications of Coded-Conversion and Excel-AI-CPAT (2a, 2b, 2c)

### Tasks and Milestones

| Code | Task / milestone | Days | From | To | Status |
| --- | --- | --- | --- | --- | --- |
| 2c | Planning and Egypt work | 5 | 28 Sep 2026 | 2 Oct 2026 | Complete |
| 2b_m1 | Completion of Zoe's FTT project |  |  | 27 Nov 2026 | Open |
| 2c | Pathways tool integration (CPAT-SiSePuede) | 5 | 4 Jan 2027 | 8 Jan 2027 | Planned |
| 2c | Pilot country projects | 5 | 11 Jan 2027 | 15 Jan 2027 | Planned |
| 2c_m1 | Delivery of pathways tool (complete) |  |  | 15 Jan 2027 | Open |
| 2b | Existing models: FTT and MFMod (tbc) on one Python platform | 5 | 8 Feb 2027 | 12 Feb 2027 | Planned |
| 2b_m2 | Delivery of existing models working smoothly: FTT and MFMod (tbc) |  |  | 12 Feb 2027 | Open |
| 2a | Excel-AI-CPAT with GHG accounting MVP, including the Total Carbon Price | 5 | 15 Feb 2027 | 19 Feb 2027 | Planned |
| 2a | Application to GHG accounting, crediting and FFI | 10 | 22 Feb 2027 | 5 Mar 2027 | Planned |
| 2a_m1 | Delivery of the application to GHG accounting, crediting and FFI |  |  | 5 Mar 2027 | Open |
|  | Total | 35 |  |  |  |

### Implementation

2a  The Excel-AI-CPAT GHG accounting MVP, with the Total Carbon Price, in the week of 15 February; the application to GHG accounting, crediting and FFI over two weeks from 22 February, delivered by 5 March (2a_m1).

2b  One week from 8 February, delivered by 12 February (2b_m2), after Zoe's FTT project completes on 27 November (2b_m1).

2c  Planning and Egypt work in the week of 28 September; pathways integration in the week of 4 January and pilot country projects in the week of 11 January, with the pathways tool complete by 15 January (2c_m1). Pathways integration covers translating between CPAT and SiSePuede outputs, in particular integrating the CPAT air pollution model, and finalizing a policy interface to the joint tool, including carbon taxation and public investment. The CPAT-LTS investment approach enters the tool in versions: V1 process emissions for CBAM sectors (with Karly, in progress) and green public investment from CCDR data (prototyped); V2 debt projections (to be agreed); V3 efficiency of public investment and energy fiscal costs and risks for finance ministries (to be agreed). Stephen's own time is limited to these weeks; the rest of the integration work is done by the CPM team under his supervision.

### Pathways Work Program (2c)

A work program with David Groves is consolidating CPAT, CPM (formerly SiSePuede; referred to as CPT/CPM within the Bank), MANAGE and MINDSET into a single country policy analysis tool, first applied in Libya, Egypt and Morocco. The initial phase, ending July 2026, covered scoping and first outputs:

- Reconciling scenario assumptions and outputs between CPAT and SiSePuede (presentation complete)

- Mapping affected variables across the two systems and comparing outputs (presentation complete)

- Running the coded CPAT system in full on the SiSePuede side (complete)

- Bringing policies and CPAT prices into CPAT–SiSePuede (partially complete)

- Setting up team Claude accounts with shared context, so AI use can grow within the SiSePuede–WB team (aiming to unlock soon)

An integrated country policy analysis tool in which coded CPAT and SiSePuede share inputs and exchange outputs:

- Prices: CPAT’s database of fuel prices, taxes and subsidies in SiSePuede, feeding all downstream models.

- Policies: carbon pricing and public investment as SiSePuede inputs, through combined scenario input files.

- Energy and emissions: CPAT’s main mitigation equations in SiSePuede, with elasticities and scenario assumptions coordinated.

- Revenue and fiscal: CPAT’s revenue calculations, with IMF fiscal projections perturbed by policy scenarios.

- Co-benefits: outputs converted in both directions between CPAT and SiSePuede, including air pollution.

- Clear assumptions: a unified database of key inputs, with online documentation.

- Public investment: marginal abatement cost information and SiSePuede’s optimized public investment linked back to CPAT-Excel.

### Uncertainties

2a  The requirements for GHG accounting, policy crediting and FFI are not yet fully set out, so the tools will adjust as they become clearer. The charge code for TF-TCAF-Crediting is still to be confirmed.

2c  Bringing policies and CPAT prices into SiSePuede is only partially complete. The CPAT price database should still be verified by country teams. The team’s shared AI set-up is not yet in place. Versions V2 and V3 of the investment approach are still to be agreed.

### Requirements and Resources

- 2a Requirements for GHG accounting, policy crediting and FFI

- 2c CPAT Prices Database; CPAT SiSePuede repo; CPAT Input Policies Matrix; Data mappings folder

## Objective Three: Other Tools - Tax and Macro-Fiscal Dashboard, Excise Diagnostic and Energy GP cross-support (3a, 3b, 3c)

### Tasks and Milestones

| Code | Task / milestone | Days | From | To | Status |
| --- | --- | --- | --- | --- | --- |
| 3a/3b | Excise Diagnostic and Tax and Macro-Fiscal Dashboard: proofs of concept | 10 | 13 Jul 2026 | 31 Jul 2026 | Complete |
| 3a/3b | Excise Diagnostic and Tax and Macro-Fiscal Dashboard: MVPs built | 15 | 31 Aug 2026 | 25 Sep 2026 | Complete |
| 3a_m1 | Delivery of Excise Diagnostic MVP |  |  | 25 Sep 2026 | Complete |
| 3b_m1 | Delivery of Tax and Macro-Fiscal Dashboard MVP |  |  | 25 Sep 2026 | Complete |
| 3a | Excise Diagnostic: build handover pack | 5 | 12 Oct 2026 | 16 Oct 2026 | Complete |
| 3a_m2 | Delivery of Excise Diagnostic to Dirk |  |  | 16 Oct 2026 | Complete |
| 3b | Tax and Macro-Fiscal Dashboard: build handover pack | 5 | 19 Oct 2026 | 23 Oct 2026 | Complete |
| 3b_m2 | Delivery of Tax and Macro-Fiscal Dashboard to Dirk |  |  | 23 Oct 2026 | Complete |
| 3a/3b | Follow-up support to Dirk: Excise Diagnostic and Tax and Macro-Fiscal Dashboard | 5 | 8 Mar 2027 | 12 Mar 2027 | Planned |
| 3c | Energy GP cross-support (tbc) | 0 | Not slotted |  | Not funded |
|  | Total | 40 |  |  |  |

### Implementation

The MVPs were built in July (two weeks) and September (three weeks). Each tool then gets its own week to build a handover pack (code, data, audit trail, user guide and example scripts, so others can use and extend it; for 3a also the working paper and process specification), in a format agreed with Dirk, and is delivered to Dirk at the end of that week: 3a on 16 October and 3b on 23 October. Follow-up support (3a/3b) is from 8 March. Energy GP cross-support (3c, tbc) would run in parallel, only if funded; the plan assumes none.

### Uncertainties

The handover format is not yet agreed with Dirk, nor who in the team will own each tool. The tools are MVPs and have not been validated. Energy GP cross-support (tbc) depends on funding that is not yet confirmed.

### Requirements and Resources

- 3a/3b Handover format and date agreed with Dirk; a named owner in the team for each tool

- 3a Excise Diagnostic working paper and process specification

- 3c Confirmed Energy GP funding (tbc), if the cross-support goes ahead

## Related Documents

- CPAT Validation — validation needs for the team (out of scope)

- Publications — research papers (personal research supporting career objectives, done in August 2026 leave without pay) and dissemination plan

- Master plan (Stephen_FY27_Master_Plan_v3.2.xlsx) — the workbook for sequencing, funding, milestones and the week ahead; it follows this plan, which is the master

- Slide deck (Use of AI in developing climate fiscal tools; AIClimate-FiscalTools_v2.5.pptx) — the summary for discussion: products, use of AI, timelines and division of labor

- User guides (Presentations - Tools folder) — for 3a and 3b, drafted 30 September