## Slide 1
CPAT · CONSOLIDATED SUMMARY · SEPTEMBER 2026
A new CPAT engine, and what we build on it
The problem, the coded and AI-Excel conversion, other products, and what to keep
AI-Excel
Coded: Python + Shiny
Other products
Stephen Stretton · World Bank
Notes: A summary of two decks: Issues with CPAT and Options for Remediation (first presented April 2026) and the Coded CPAT and AI-Excel plan (September 2026), plus a keep-or-drop review against the FY27 work plan.

## Slide 2
Contents
PART 1 · SLIDES 3–4
The problem
Why CPAT's mitigation module needs a new engine
PART 2 · SLIDES 5–10
Coded CPAT and AI-Excel
Two forms of one engine, how they stay equal, risks, timeline, and where each goes
PART 3 · SLIDES 11–15
Other products
CPAT–SiSePuede, a single Python platform, a dashboard and policy report, and the Total Carbon Price into GHG accounting
PART 4 · SLIDE 16 · CONCLUSION · 17
What to keep and what to drop
A review against the FY27 work plan, then the conclusion and next steps
CPAT consolidated summary · 2

## Slide 3
PART 1 · THE PROBLEM
The mitigation module is heavy, slow and hard to trust
Code quality
250,000+ cells, never checked for bugs
The largest module; others wait on it
Excel, Python and docs drift apart
Validation
Not published on the WB side
IMF side rests mostly on an elasticity meta-analysis
Last WB validation work was in 2022/23
Usability
Can take ten minutes to load
Hard to demo; some bugs
Power model too complex
Source: Issues with CPAT and Options for Remediation (April 2026) · CPAT consolidated summary · 3

## Slide 4
PART 1 · THE PROBLEM
Patching the old Excel will not be enough
The April option
A new engine tab in legacy CPAT
Lambda functions, arrays and simpler prices. Result: a more consistent engine, but CPAT not much faster or smaller.
What the engine must now do
Policy mixes across every sector, fuel and policy
A clean back end for the new WB–IMF interface
GHG accounting, with every figure traceable
So: rebuild the engine with AI, in code and in Excel, and keep them equal.
CPAT consolidated summary · 4

## Slide 5
PART 2 · CODED CPAT AND AI-EXCEL
One set of equations, two forms
 | Coded (Python + Shiny) | AI-Excel
What it is | The core engine in Python, with an online Shiny interface | A cut-down CPAT in Excel, built from scratch with AI
Users | Modelers and teams who run code; web users via Shiny | Economists who work in Excel; IMF and WB CPAT teams
Strength | Scales, tests and links to other Python models | Familiar, transparent cell by cell, easy to audit
Limit | Not open to non-coders without Shiny | Harder to scale; LAMBDA needs a recent Excel
CPAT consolidated summary · 5
Notes: Both forms share one set of equations and are built component by component, together: mitigation basics, distribution, power, air pollution, the rest of mitigation, transport.

## Slide 6
PART 2 · THE CASE FOR AI-EXCEL
AI-Excel serves three purposes
1
Input to the WB–IMF process
Agreed with Dirk: a contributor to future development, not yet the full CPAT.
2
GHG accounting and policy crediting
A transparent tool for ex-ante DPF accounting, where each figure is traceable.
3
Cross-checking
An independent check on the coded engine and on legacy CPAT.
CPAT consolidated summary · 6

## Slide 7
PART 2 · MAINTAINABILITY
Scripts keep code, Excel and docs equal
Excel CPAT
Legacy data and parameters
Extraction scripts
Pull data out, with a source trail
Generative files
Build script + pseudocode
Python engine
AI-Excel
Documentation
Share generators, not context
We save the full build script and a readable pseudocode version that produces it.
Works with Claude or Copilot
Any AI coding tool can pick it up; proprietary data stays ring-fenced.
CPAT consolidated summary · 7

## Slide 8
PART 2 · ISSUES AND RESOLUTIONS
The main risks are known and manageable
Topic | Issue | Resolution
IMF ownership | The IMF may want to take control, and could build its own version. | Agree the WB side first, then bring the IMF in early. Their version may look like ours.
Compatibility | LAMBDA functions need recent Excel; older copies, e.g. in finance ministries, may fail. | Finance ministries are not the first audience. LAMBDAs can be turned back into direct formulae.
Functionality | Excel CPAT holds many ad hoc changes; the new model will not match them all at first. | Build a sound, maintainable base; extend it once code and AI-Excel are adequate.
Scope | Risk of two Excel models to maintain in the long run. | A contributor to the WB–IMF process, not yet the full CPAT. Long-term, keep one Excel.
Accessibility | Teams use different AI tools, and some data is proprietary. | Works with Claude or GitHub Copilot; proprietary data kept ring-fenced.
CPAT consolidated summary · 8

## Slide 9
PART 2 · MASTER TIMELINE²
Excel MVP¹ by 16 October; all modules by February
Model + AI-Excel
Shiny + code
Application
Other products
Oct
Nov
Dec
Leave
Jan
Feb
Mar
5
12
19
26
2
9
16
23
30
7
14
4
11
18
25
1
8
15
22
1
8
15
Mitigation basics + Excel MVP¹
Code MVP + Shiny
Distribution
Power
Air pollution
Remainder of mitigation
Shiny prototype
GHG accounting
Transport
Policy crediting and FFI
Macro-fiscal dashboard updates
Policy reports
MVP · 16 Oct
¹ MVP = minimum viable product: mitigation basics working, and matching, in code and AI-Excel. Hatched = leave.
² In parallel, not shown: CPAT–SiSePuede supervision (half a day a week to mid-Dec, a day a week in Jan); Python platform with Zoe (Feb, about half of each week); Energy GP finance model review (two weeks, late Jan–Feb, not yet slotted).
Week-of dates · CPAT consolidated summary · 9
Notes: Done so far (July and September, five weeks): prices proof of concept, AI dashboard and Excise Diagnostic proofs of concept, requirements and AI coding set-up, and the AI-Excel form begun. The week of 26 October is now leave, so distribution takes one week (2 November); all later dates are unchanged.

## Slide 10
PART 2 · WHERE THE CODE AND THE EXCEL GO
The code feeds SiSePuede; the Excel feeds the WB–IMF process
One engine
One set of equations, kept equal by script
Coded (Python)
With a Shiny web interface
AI-Excel
A cut-down CPAT in Excel
CPAT–SiSePuede pathways tool · slide 12
Single Python platform with MFMod and FTT · slide 13
Model comparison and web users via Shiny
WB–IMF CPAT process, as a contributor
GHG accounting and policy crediting tool
Cross-check of the code and legacy CPAT
CPAT consolidated summary · 10
Notes: The transition to Part 3. The coded engine is the input to the CPAT–SiSePuede project and sits on the single Python platform. AI-Excel goes to the WB–IMF process, GHG accounting and cross-checking. Part 3 starts with the two places the code goes.

## Slide 11
PART 3 · OTHER PRODUCTS
Small tasks, built on what already exists
Little change is proposed, as there is not time this FY: just tweaks to what is already there.
 | Product | Starting point (exists) | Tweak proposed | Slide
A | CPAT–SiSePuede | Coded CPAT runs in full on the SiSePuede side | Supervise the CPM team: prices, policies, air pollution | 12
B | Single Python platform | CPAT, MFMod-Python and FTT | One place to run them, with one user guide | 13
C | Dashboard and policy issue report | Excise Diagnostic; AI macro-fiscal dashboard | Add tax indicators; frame reports by issue | 14
D | Total Carbon Price into GHG accounting | Current Total Carbon Price | Link to the GHG accounting metric; standalone | 15
CPAT consolidated summary · 11

## Slide 12
PART 3 · A · CPAT–SISEPUEDE
Coded CPAT goes into the country pathways tool
With David Groves: CPAT, CPM (formerly SiSePuede), MANAGE and MINDSET combined into one country policy analysis tool.
Done · first phase, to July 2026
Assumptions and outputs reconciled
Variables mapped and outputs compared
Coded CPAT runs in full on the SiSePuede side
Prices and policies partly brought in
This year · supervising the CPM team
Finish prices, policies and the air pollution translation
CPAT-LTS investment approach and policy interface
Light touch: about half a day a week, a day a week in January
CPAT consolidated summary · 12

## Slide 13
PART 3 · B · SINGLE PYTHON PLATFORM
Make existing models easy to use, not develop them further
What
CPAT, MFMod-Python and FTT, as they are today, on one common platform.
How
A shared set-up and one user guide. FTT made ready to run, with data aligned to CPAT countries.
Not
No further model development, and no full merging of FTT or MFMod into CPAT.
CPAT consolidated summary · 13

## Slide 14
PART 3 · C · DASHBOARD AND POLICY ISSUE REPORT
Two prototypes become two products
Prototype · done
Excise Diagnostic
Country tax system: excises, subsidies, electricity pricing
Prototype · done
Macro-fiscal indicators
AI dashboard with a full data audit trail
Brought together
Output 1
Dashboard
Macro-fiscal indicators, now with excise and other tax indicators, and the Total Carbon Price
Output 2
Policy issue report
One issue in one country, e.g. feebates: the situation, best practice and reform
CPAT consolidated summary · 14

## Slide 15
PART 3 · D · TOTAL CARBON PRICE INTO GHG ACCOUNTING
Bring the Total Carbon Price into GHG accounting
A standalone product
Delivered on its own, not as part of Coded CPAT.
Linked to GHG accounting
Consistent with the GHG accounting metric.
Also in the dashboard
Shown alongside the macro-fiscal and tax indicators.
CPAT consolidated summary · 15

## Slide 16
PART 4 · WHAT TO KEEP AND WHAT TO DROP
The plan is full to 20 March: anything added must replace something
KEEP · CORE
Coded CPAT and AI-Excel. Funded; the base for everything else
GHG accounting. A corporate requirement; no DPF tool exists
CPAT–SiSePuede. Funded; light-touch supervision
KEEP · SMALL
Python platform. Access only
Dashboard and policy report. Prototypes exist; funding to confirm
Policy crediting and FFI. One week, on GHG accounting
Total Carbon Price into GHG accounting. Not yet scheduled
Energy GP code help. Not on the timeline; needs a slot
DROP OR DEFER
Patching legacy Excel (new tab, Lambdas): superseded
Validating legacy CPAT: separate note
Full CPAT replacement; merging FTT or MFMod: later
April items not in FY27 plan: ETS pilot, downstream pricing, CPAT paper
Source: FY27 work plan v1.1 (28 Sept 2026) · CPAT consolidated summary · 16
Notes: For discussion. The work plan selects GHG accounting (3a) and marks policy crediting (3b) and the tax/fiscal dashboard (3c) as possibly dropped, at five weeks each. The master timeline gives them much less: one week for policy crediting and FFI, two weeks each for the dashboard and policy reports. The Energy GP coding help (3d, two weeks) is in the work plan but not on the master timeline, so it needs a slot or should go. The April items (ETS pilot, downstream industrial pricing, CPAT working paper) do not appear in the FY27 plan; confirm whether they are done, handed over or dropped.

## Slide 17
CONCLUSION
One AI-built engine, two forms, a few small products
Fixes the module's problems
A compact, traceable engine replaces 250,000+ cells and handles policy mixes.
Each form has a home
Code into SiSePuede and the Python platform; AI-Excel into the WB–IMF process and GHG accounting.
Focus wins
Keep the core; other products are small tweaks or wait.
NEXT STEPS
Informal chats in the office before 16 October
Excel and coded MVP by 16 October
Agree on the WB side, then bring the IMF in
Confirm GHG accounting and policy crediting requirements
Agree the keep-or-drop list
Choose a country project (to be defined)
CPAT consolidated summary · 17