## Slide 1
CPAT · EXTENDED SUMMARY · SEPTEMBER 2026
A new CPAT engine, and what we build on it
Issues with CPAT, the coded and AI-Excel conversion, other products, and what to keep
AI-Excel
Coded: Python + Shiny
Other products
Stephen Stretton · World Bank
Notes: An extended version of the consolidated summary. It draws on Issues with CPAT and Options for Remediation (first presented April 2026), the Coded CPAT and other AI tools plan (September 2026) and the FY27 work plan.

## Slide 2
Contents
PART 1 · SLIDES 3–8
The problem
Three problems
Inside the module
Main coding issues
Approach by component
Why a patch is not enough
PART 2 · SLIDES 9–17
Coded CPAT and AI-Excel
Why convert
Two products compared
Purposes of AI-Excel
Maintainability
Issues and resolutions
Status and timeline
Where each form goes
PART 3 · SLIDES 18–26
Other products
Overview (19)
A · CPAT–SiSePuede (20)
B · Python platform (21)
C · Dashboard and policy report (22–25)
D · Total Carbon Price into GHG accounting (26)
PART 4 · SLIDES 27–28
Keep, drop and conclude
What to keep and what to drop
Conclusion and next steps
CPAT extended summary · 2

## Slide 3
PART 1
The problem
Why CPAT's mitigation module needs a new engine, drawn from Issues with CPAT and Options for Remediation
CPAT extended summary · 3

## Slide 4
PART 1 · THE PROBLEM
CPAT's mitigation module has three problems
Code quality
The module is large, slow, heavy and hard to maintain. No user can understand or validate 250,000+ spreadsheet cells.
Empirical validation
The WB side has not published CPAT. The IMF publication relies mostly on an elasticity meta-analysis.
Short-term usability
A few bugs, and hard to demonstrate: it can take ten minutes to load. This limits its use in country work.
CPAT extended summary · 4

## Slide 5
PART 1 · INSIDE THE MITIGATION MODULE
The module has eight components
1 · Processing inputs
2 · Price tables
3 · Main fuel use model
4 · Engineering power model
5 · Engineering transport model
6 · Revenue and GDP
7 · Emissions accounting
8 · Processing results for presentation
Main calculation engine
Components 3–7, repeated twice: once for the baseline and once for the policy scenario.
CPAT extended summary · 5

## Slide 6
PART 1 · MAIN CODING ISSUES
Heavy, slow and hard to keep consistent
Heavy
The mitigation module is the largest part of CPAT.
Slow
Other modules depend on it, so they wait for it.
Hard to maintain
250,000+ cells are hard to understand and validate.
Hard to keep consistent
Excel, Python CPAT and documentation drift apart; a spreadsheet is hard to publish in a peer-reviewed journal.
Not fit for the new UI
Policy mixes need every sector and fuel combination handled properly: a fully consistent approach.
CPAT extended summary · 6

## Slide 7
PART 1 · COMPONENT AND APPROACH
Recode the fuel use model first, then power
Component | Approach
Processing inputs | Later (depends on the main model)
Price tables | Largely as now; recoded with AI for proof of concept and checking
Main fuel use model (main focus) | AI-assisted recoding with Lambda functions and arrays
Engineering power model (secondary) | AI-assisted recoding with Lambda functions and arrays
Engineering transport model | Later
Emissions accounting | Air pollution array calculation: a major chance to automate
Processing results for presentation | Largely as now
CPAT extended summary · 7

## Slide 8
PART 1 · WHY A PATCH IS NOT ENOUGH
Patching the old Excel will not be enough
The April option
A new engine tab in legacy CPAT
Lambda functions, arrays and simpler prices. Result: a more consistent engine, but CPAT not much faster or smaller.
What the engine must now do
Policy mixes across every sector, fuel and policy
A clean back end for the new WB–IMF interface
GHG accounting, with every figure traceable
So: rebuild the engine with AI, in code and in Excel, and keep them equal.
CPAT extended summary · 8

## Slide 9
PART 2
The coded conversion and AI-Excel
Two forms of one engine, how they stay equal, the risks, the timeline, and where each goes
CPAT extended summary · 9

## Slide 10
PART 2 · WHY CONVERT
A new front end is being built on an old back end
The engine is hard to change
The WB–IMF user interface is new, but the calculations sit in one large legacy Excel file. Formulae are hard to trace and adjust.
New uses need a clear engine
GHG accounting for DPFs and policy crediting need every figure traced to an equation, a parameter and a source.
AI makes one model cheap to keep
With AI, code, Excel and documentation can be updated at once. In the long run we want one Excel, not several.
CPAT extended summary · 10
Notes: The core point: an AI-codable engine lets us keep code, Excel and documentation in step automatically. That is what makes two forms affordable now, and one model possible later.

## Slide 11
PART 2 · TWO PRODUCTS, COMPARED
One set of equations, two forms
 | 1 · Coded (Python + Shiny) | 2 · AI-Excel
What it is | The core engine in Python, with an online Shiny interface | A cut-down CPAT in Excel, built from scratch with AI
First uses | Model comparison; full country work once complete; SiSePuede and pathways tool | GHG accounting; a clean back end for the new WB–IMF interface
Users | Modelers and teams who run code; web users via Shiny | Economists who work in Excel; IMF and WB CPAT teams
Strength | Scales, tests and links to other Python models | Familiar, transparent cell by cell, easy to audit
Limit | Not open to non-coders without Shiny | Harder to scale; LAMBDA needs a recent Excel
CPAT extended summary · 11
Notes: Both forms share one set of equations and are kept equivalent by script. Each is built component by component, together: distribution, mitigation basics, power, other mitigation and GDP, air pollution, transport.

## Slide 12
PART 2 · THE CASE FOR AI-EXCEL
AI-Excel serves three purposes
1
Input to the WB–IMF process
Agreed with Dirk: a contributor to future development, not yet the full CPAT. A base for one maintainable model.
2
GHG accounting and policy crediting
A transparent Excel tool for ex-ante DPF accounting and crediting, where each figure is traceable.
3
Cross-checking
An independent check on the coded engine and on legacy CPAT. Differences point to errors on either side.
CPAT extended summary · 12
Notes: AI-Excel also lowers the risk of building a new user interface on an archaic back end. It is not meant to replace legacy CPAT yet; that is for later discussion.

## Slide 13
PART 2 · MAINTAINABILITY
Scripts keep code, Excel and docs equal
Excel CPAT
Legacy data and parameters
Extraction scripts
Pull data out, with a source trail
Generative files
Build script + pseudocode
Python engine
AI-Excel
Documentation
Share generators, not context
Claude builds the Excel through a Python script. We save (a) that full script and (b) a readable pseudocode version that produces it.
Works with Claude or Copilot
Any AI coding tool can pick it up. Proprietary data stays ring-fenced outside the shared files.
CPAT extended summary · 13
Notes: Joint working with AI: rather than passing around long context, we keep small generative files and concise scripts. Anyone, with any AI tool, can regenerate the Excel, the code and the documentation from them.

## Slide 14
PART 2 · ISSUES AND RESOLUTIONS
The main risks are known and manageable
Topic | Issue | Resolution
IMF ownership | The IMF may want to take control, and could build its own version. | Agree the WB side first, then bring the IMF in early. Their version may look like ours.
Compatibility | LAMBDA functions need recent Excel; older copies, e.g. in finance ministries, may fail. | Finance ministries are not the first audience. LAMBDAs can be turned back into direct formulae.
Functionality | Excel CPAT holds many ad hoc changes; the new model will not match them all at first. | Build a sound, maintainable base; extend it once code and AI-Excel are adequate.
Scope | Risk of two Excel models to maintain in the long run. | A contributor to the WB–IMF process, not yet the full CPAT. Long-term, keep one Excel.
Accessibility | Teams use different AI tools, and some data is proprietary. | Works with Claude or GitHub Copilot; proprietary data kept ring-fenced.
CPAT extended summary · 14
Notes: Ask the room: what other issues should we plan for? These points come from discussion with Dirk.

## Slide 15
PART 2 · CURRENT STATUS · 28 SEPTEMBER
Five weeks spent; the proofs of concept are done
July · 2 weeks · done
Proofs of concept
Coded CPAT prototype, proof of concept on prices
AI dashboard, with full data audit trail
Excise Diagnostic
September · 3 weeks · done
Set-up
Requirements and scope
AI coding set-up
AI-Excel form begun
Pathways tool · in progress
CPAT and SiSePuede
Assumptions reconciled; variables mapped
Coded CPAT run in full on the SiSePuede side
Prices and policies partly brought in
Blocked by leave to 14 July and through August (leave without pay). Next: mitigation basics and the Excel MVP, from 5 October.
Source: FY27 work plan v1.1 · CPAT extended summary · 15

## Slide 16
PART 2 · MASTER TIMELINE²
Excel MVP¹ by 16 October; all modules by February
Model + AI-Excel
Shiny + code
Application
Other products
Oct
Nov
Dec
Leave
Jan
Feb
Mar
5
12
19
26
2
9
16
23
30
7
14
4
11
18
25
1
8
15
22
1
8
15
Mitigation basics + Excel MVP¹
Code MVP + Shiny
Distribution
Power
Air pollution
Remainder of mitigation
Shiny prototype
GHG accounting
Transport
Policy crediting and FFI
Macro-fiscal dashboard updates
Policy reports
MVP · 16 Oct
¹ MVP = minimum viable product: mitigation basics working, and matching, in code and AI-Excel. Hatched = leave.
² In parallel, not shown: CPAT–SiSePuede supervision (half a day a week to mid-Dec, a day a week in Jan); Python platform with Zoe (Feb, about half of each week); Energy GP finance model review (two weeks, late Jan–Feb, not yet slotted).
Week-of dates · CPAT extended summary · 16
Notes: Done so far (July and September, five weeks): prices proof of concept, AI dashboard and Excise Diagnostic proofs of concept, requirements and AI coding set-up, and the AI-Excel form begun. The week of 26 October is now leave, so distribution takes one week (2 November); all later dates are unchanged.

## Slide 17
PART 2 · WHERE THE CODE AND THE EXCEL GO
The code feeds SiSePuede; the Excel feeds the WB–IMF process
One engine
One set of equations, kept equal by script
Coded (Python)
With a Shiny web interface
AI-Excel
A cut-down CPAT in Excel
CPAT–SiSePuede pathways tool · slide 20
Single Python platform with MFMod and FTT · slide 21
Model comparison and web users via Shiny
WB–IMF CPAT process, as a contributor
GHG accounting and policy crediting tool
Cross-check of the code and legacy CPAT
CPAT extended summary · 17
Notes: The transition to Part 3. The coded engine is the input to the CPAT–SiSePuede project and sits on the single Python platform. AI-Excel goes to the WB–IMF process, GHG accounting and cross-checking. Part 3 starts with the two places the code goes.

## Slide 18
PART 3
Other products
Small tasks built on what exists: CPAT in SiSePuede, a single Python platform, a dashboard and policy issue report, and the Total Carbon Price into GHG accounting
CPAT extended summary · 18

## Slide 19
PART 3 · OTHER PRODUCTS
Small tasks, built on what already exists
Little change is proposed, as there is not time this FY: just tweaks to what is already there.
 | Product | Starting point (exists) | Tweak proposed | Slide
A | CPAT–SiSePuede | Coded CPAT runs in full on the SiSePuede side | Supervise the CPM team: prices, policies, air pollution | 20
B | Single Python platform | CPAT, MFMod-Python and FTT | One place to run them, with one user guide | 21
C | Dashboard and policy issue report | Excise Diagnostic; AI macro-fiscal dashboard | Add tax indicators; frame reports by issue | 22–25
D | Total Carbon Price into GHG accounting | Current Total Carbon Price | Link to the GHG accounting metric; standalone | 26
CPAT extended summary · 19

## Slide 20
PART 3 · A · CPAT–SISEPUEDE
Coded CPAT goes into the country pathways tool
With David Groves: CPAT, CPM (formerly SiSePuede), MANAGE and MINDSET combined into one country policy analysis tool.
Done · first phase, to July 2026
Assumptions and outputs reconciled
Variables mapped and outputs compared
Coded CPAT runs in full on the SiSePuede side
Prices and policies partly brought in
This year · supervising the CPM team
Finish prices, policies and the air pollution translation
CPAT-LTS investment approach and policy interface
Light touch: about half a day a week, a day a week in January
CPAT extended summary · 20

## Slide 21
PART 3 · B · SINGLE PYTHON PLATFORM
Make existing models easy to use, not develop them further
What
CPAT, MFMod-Python and FTT, as they are today, on one common platform.
How
A shared set-up and one user guide. FTT made ready to run, with data aligned to CPAT countries.
Not
No further model development, and no full merging of FTT or MFMod into CPAT.
CPAT extended summary · 21

## Slide 22
PART 3 · C · PROTOTYPE 1: EXCISE DIAGNOSTIC
AI maps a country's energy tax system
Step 1
Generate the tax system
Excises on fuels and energy
Fossil fuel subsidies
Electricity pricing arrangements
Step 2
Generate metrics
For example: effective carbon rates
Price gaps and subsidy costs
Revenue at stake, run through the engine
CPAT extended summary · 22
Notes: Proof of concept done in July. Every fact carries a source, so country teams can check it. The metrics listed are examples; the final set is to be agreed.

## Slide 23
PART 3 · C · PROTOTYPE 2: MACRO-FISCAL INDICATORS
The interface in development
A country profile
Kenya shown: 35 of 35 indicators with data
Grouped by question
Fossil revenue, mitigation cost, fiscal space, investment, cost of capital, finance
Scored and sourced
Each indicator rated, scored out of 10, with year and coverage
CPAT extended summary · 23
Notes: AI-built dashboard proof of concept, with a full data audit trail. The tax indicators from the Excise Diagnostic join this base.

## Slide 24
PART 3 · C · DASHBOARD AND POLICY ISSUE REPORT
Two prototypes become two products
Prototype · done
Excise Diagnostic
Country tax system: excises, subsidies, electricity pricing
Prototype · done
Macro-fiscal indicators
AI dashboard with a full data audit trail
Brought together
Output 1
Dashboard
Macro-fiscal indicators, now with excise and other tax indicators, and the Total Carbon Price
Output 2
Policy issue report
One issue in one country, e.g. feebates: the situation, best practice and reform
CPAT extended summary · 24

## Slide 25
PART 3 · C · POLICY ISSUE REPORT
One issue, one country, for example feebates
1
The situation
Where the country stands on the issue, drawn from the dashboard and diagnostic.
2
Best practice
The best policy design, and what other countries did and learned.
3
Reform
The opportunities for reform in that country, and how to get there.
CPAT extended summary · 25
Notes: The dashboard says what is there; the policy issue report says what to do next. Together they give a fast, sourced starting point for policy dialogue.

## Slide 26
PART 3 · D · TOTAL CARBON PRICE INTO GHG ACCOUNTING
Bring the Total Carbon Price into GHG accounting
A standalone product
Delivered on its own, not as part of Coded CPAT.
Linked to GHG accounting
Consistent with the GHG accounting metric.
Also in the dashboard
Shown alongside the macro-fiscal and tax indicators.
CPAT extended summary · 26

## Slide 27
PART 4 · WHAT TO KEEP AND WHAT TO DROP
The plan is full to 20 March: anything added must replace something
KEEP · CORE
Coded CPAT and AI-Excel. Funded; the base for everything else
GHG accounting. A corporate requirement; no DPF tool exists
CPAT–SiSePuede. Funded; light-touch supervision
KEEP · SMALL
Python platform. Access only
Dashboard and policy report. Prototypes exist; funding to confirm
Policy crediting and FFI. One week, on GHG accounting
Total Carbon Price into GHG accounting. Not yet scheduled
Energy GP code help. Not on the timeline; needs a slot
DROP OR DEFER
Patching legacy Excel (new tab, Lambdas): superseded
Validating legacy CPAT: separate note
Full CPAT replacement; merging FTT or MFMod: later
April items not in FY27 plan: ETS pilot, downstream pricing, CPAT paper
Source: FY27 work plan v1.1 (28 Sept 2026) · CPAT extended summary · 27
Notes: For discussion. The work plan selects GHG accounting (3a) and marks policy crediting (3b) and the tax/fiscal dashboard (3c) as possibly dropped, at five weeks each. The master timeline gives them much less: one week for policy crediting and FFI, two weeks each for the dashboard and policy reports. The Energy GP coding help (3d, two weeks) is in the work plan but not on the master timeline, so it needs a slot or should go. The April items (ETS pilot, downstream industrial pricing, CPAT working paper) do not appear in the FY27 plan; confirm whether they are done, handed over or dropped.

## Slide 28
CONCLUSION
One AI-built engine, two forms, a few small products
Fixes the module's problems
A compact, traceable engine replaces 250,000+ cells and handles policy mixes.
Each form has a home
Code into SiSePuede and the Python platform; AI-Excel into the WB–IMF process and GHG accounting.
Focus wins
Keep the core; other products are small tweaks or wait.
NEXT STEPS
Informal chats in the office before 16 October
Excel and coded MVP by 16 October
Agree on the WB side, then bring the IMF in
Confirm GHG accounting and policy crediting requirements
Agree the keep-or-drop list
Choose a country project (to be defined)
CPAT extended summary · 28