## Slide 1
1 · PROPOSAL
One Python platform for fiscal policy, built around the new CPAT
Stephen Stretton · meeting with Sebastian · 20 Oct 2026 · 1
WHY
• One code base for climate-related fiscal policy, shared with the macro unit
• A PFR process: energy costs, fiscal risks, spending efficiency, tax changes
• One country run end to end: data in, results back on one page
• Replaces one-off spreadsheets; every number traceable
• Lite versions now; MFMod and full IMF tools as cross-checks
ENGINE
Coded CPAT (new CPAT)
• Prices, revenue, emissions, households
• Excel-AI v6.2 is the checked reference
Python final 11 Dec
DATA
Tax & Macro-Fiscal Dashboard
• 64 indicators, 11 blocks, 217 countries
• Now with macro-model inputs and results
Built; handed to Dirk
NEEDS
Investment needs + CDPM
• NMIM: budget need path 2025-50, who pays
• CDPM pathways (formerly SiSePuede)
NMIM v0.2; CDPM Jan
POLICY
Pricing and tax tools
• Price feasibility (F1-F3): tax vs feebate
• Excise, CBAM, crediting / FFI
v0.1 to v3.0
MACRO AND DEBT
GIMF / DIGNAD / DIGNAR-lite
• Chosen by country type
• LIC-DSF-lite debt verdict; MFMod option
v0.1, 186 countries run
TECHNOLOGY
FTT national
• Technology diffusion on CPAT's countries
• FTT + MFMod on one platform
27 Nov; 12 Feb
So: most components exist; the platform is one repo, one guide, one calibration and one country chain joining them.

## Slide 2
2 · THE UPGRADE
Macro-fiscal block: built this month, an upgrade to the new CPAT
CDPM = the model formerly called SiSePuede. · Stephen Stretton · meeting with Sebastian · 20 Oct 2026 · 2
Dashboard
Data in
Needs (NMIM)
Budget need
Price feasibility
Pricing revenue
GIMF / DIGNAD / DIGNAR
GDP, fiscal path
LIC-DSF-lite
Debt verdict
Dashboard
Results back
Piece | Status (20 Oct) | Upgrade to the new CPAT
GIMF-lite / DIGNAD-lite | v0.1; one shared calibration from the dashboard; routed by country type | Replaces CPAT's fixed fiscal multipliers with a model of GDP, prices and fiscal path
DIGNAR-lite (resource-rich) | Built; fossil rents fall 80% by 2050 as the world decarbonises | New: stranded fossil revenue as a fiscal risk
Debt test (LIC-DSF-lite) | Built; 5 of 66 LIC/LMIC ratings worsen with the programme; coefficients to check | Replaces the planned debt equation (investment approach V2)
Public spending efficiency | PEFA/PIMA-mapped efficiency in the calibration; spending split from capital | Investment approach V3; next: PIMA scores, absorptive capacity, execution
CDPM pathways | Edmundo on track; coded CPAT to CDPM in Dec; pilots Jan | Physical pathways and costs feeding the needs step
Integrated run | 186 countries: 135 GIMF, 35 DIGNAD, 16 DIGNAR; 184 solve, 2 not financeable | One country chain; results block in the dashboard
Caveats: calibrations illustrative; pricing revenue power-only; CPAT not yet in the chain (next: feed CPAT prices and revenue to the pricing step); not a substitute for a full DSA or MFMod.

## Slide 3
3 · CORE ENGINE
CPAT in Excel-AI and Python: ahead on build; Python is the work
Stephen Stretton · meeting with Sebastian · 20 Oct 2026 · 3
v6.2
Excel-AI MVP, 20 Oct: mitigation, power, distribution, GDP, NDC; 56 tabs
123
legacy CPAT bugs fixed, none copied; fix plans for the CPAT team
0 errors
quick check; 12,992 output codes stable; every figure traceable
57 tests
coded CPAT runs end to end; Shiny app has six sections
EXCEL-AI-CPAT
Status and next
• Power and distribution built ahead of plan (Oct, not Nov-Dec)
• Usable in 15 minutes: open, change a policy, run scenarios
• Next: Excel 365 review; data requests; send fix plans
• Final 4 Dec (50%); MVP due 23 Oct (70%)
Milestones 1a_m1, 1a_m2
CODED CPAT (PYTHON)
Status and next
• About 20,000 lines; mitigation and distribution; legacy export
• Port the validated Excel logic; fix revenue units
• Feeds CDPM pathways and the fiscal platform
• Final 11 Dec (10%); Shiny app 5 Feb
Milestones 1b_m1, 1c_m1

## Slide 4
4 · OTHER PIECES
Everything else, in one table
Stephen Stretton · meeting with Sebastian · 20 Oct 2026 · 4
Piece | Status | Next / date | Ask
Excise Diagnostic | SLE, UGA, LBR; handed to Dirk 16 Oct | Support 8-12 Mar | Owner; extend or fold into platform?
Tax & Macro-Fiscal Dashboard | Handed to Dirk; now 64 indicators | Support 8-12 Mar | Owner
CBAM policy tool | Egypt v3.0; global MVP v1.0 | No milestone | CBAM in CPAT: priority?
Crediting, GHG accounting, FFI | Planned | 15 Feb-5 Mar | Charge code; requirements
FTT national (Zoe); FTT + MFMod | Zoe delivering | 27 Nov; 12 Feb | MFMod in or out
Pathways with CDPM (Edmundo) | Meeting went well 19 Oct; repo created | Pilots 11-15 Jan | Agree cost split
Adaptation | DIGNAD-lite has adaptation capital and disasters | Not in plan | Now or FY28?
Energy GP cross-support | Not funded (16 days) | - | Funding
CDPM = the model formerly called SiSePuede. Full detail: Sebastian-Platforms-v2.pptx (appendix).

## Slide 5
5 · CONCLUSIONS
Conclusions and decisions
Stephen Stretton · meeting with Sebastian · 20 Oct 2026 · 5
CONCLUSIONS
Where we are
• The new CPAT engine is ahead of plan in Excel; Python is the next push
• A macro-fiscal block now runs every country end to end
• Together they make a single Python platform for fiscal policy and a PFR process
DECISIONS FOR YOU
What I need
• Go-ahead: the platform as the FY27 frame; the chain as the PFR process
• A pilot country (e.g. Uganda, Kenya, Egypt)
• Introduction to the macro unit (MFMod)
• What to drop to make days (no buffer to 20 Mar)
NEXT 6 WEEKS
Then
• Excel-AI MVP 23 Oct; final 4 Dec; Python 11 Dec
• Feed CPAT prices and revenue into the chain
• Check DSF coefficients; real calibrations for the pilot
• CDPM user-flow workshop (Nov)