## Slide 1: Pathways: CPAT-CDPM integration (Edmundo)
 | Status and timeline
What it is | Coded CPAT inside CDPM (formerly SiSePuede; Edmundo Molina, Tec de Monterrey; with Dave Groves and Sonya Sampson): one pathways tool
Platform | Climate platform (pathways project)
Status (20 Oct) | Edmundo meeting 19 Oct went well: on track. CPAT sent; CPAT-CDPM repo created. Egypt proof of concept close to CPAT (-7.3% vs -8.0% emissions)
Next | Integrate early (no wait for a final product); one user flow; methodology note on subsidies vs public investment
Timeline | User-flow workshop early Nov; integration 4-8 Jan; pilots (Libya, Egypt, Morocco) 11-15 Jan; end Jan
Ask / risk | Agree the methodology split (running subsidies vs upfront public investment) before integration
CDPM = the model formerly called SiSePuede. Sources: FY27 work plan v2.6; repos CPAT-AI, CPAT-CDPM, new-ai-tools; task tracker (20 Oct 2026)