## Slide 1: Climate-fiscal tools: two Python platforms
Status, timeline and asks
Stephen Stretton, meeting with Sebastian, 20 Oct 2026

## Slide 2: Summary: one code base, two platforms
• Climate policy platform (the pathways project): coded CPAT + CDPM (formerly SiSePuede) + FTT
• Fiscal policy platform: coded CPAT + MFMod-Python (macro unit) + investment needs + CBAM
  – Coded CPAT sits in both; the Excel-AI model is the checked reference
• Goal of one Python platform: work with the macro unit on a shared code base
• On track: Edmundo meeting went well (19 Oct); Excel-AI MVP due 23 Oct
• Today: agree the two platforms, the macro-unit link, and the look-ahead topics
CDPM = the model formerly called SiSePuede. Sources: FY27 work plan v2.6; repos CPAT-AI, CPAT-CDPM, new-ai-tools; task tracker (20 Oct 2026)

## Slide 3: The products at a glance
Product | Platform | Status | Next date
CPAT-AI (Excel-AI) | Reference | MVP 70%, v6.2 | 23 Oct
Coded CPAT (Python) | Both | Runs; final 10% | 11 Dec
CPAT-CDPM pathways (Edmundo) | Climate | On track | 15 Jan
FTT national (Zoe) | Climate | Zoe delivering | 27 Nov
Investment needs (NMIM) | Both | v0.2 | tbc
CBAM policy tool | Fiscal | Egypt v3.0, global v1.0 | tbc
Excise + Macro-Fiscal Dashboard | Fiscal | Handed to Dirk | 8-12 Mar
CDPM = the model formerly called SiSePuede. Sources: FY27 work plan v2.6; repos CPAT-AI, CPAT-CDPM, new-ai-tools; task tracker (20 Oct 2026)

## Slide 4: Two platforms

## Slide 5: A. Climate policy platform: the pathways project
• What: one Python tool for country decarbonisation pathways and their costs
• Parts: coded CPAT, CDPM (formerly SiSePuede; Edmundo), FTT national data (Zoe), investment needs
• Users: one integrated flow, not several tools; pilots Libya, Egypt, Morocco
• Status: Edmundo on track; Egypt proof of concept close to CPAT
• Timeline: integration 4-8 Jan; pilots 11-15 Jan; full integration end Jan
• Open: separate running subsidies from upfront public investment
CDPM = the model formerly called SiSePuede. Sources: FY27 work plan v2.6; repos CPAT-AI, CPAT-CDPM, new-ai-tools; task tracker (20 Oct 2026)

## Slide 6: B. Fiscal policy platform: with the macro unit
• What: one Python platform for climate-related fiscal policy, shared with the macro unit
• Parts: coded CPAT (revenue, prices, distribution), MFMod-Python (ModelFlow), FTT, investment needs, CBAM
• Why: MFMod handles investment, debt and growth; CPAT handles energy, prices and revenue
• Already linked: CPAT's GDP block uses MFMod fiscal multipliers
• Timeline: FTT + MFMod working 12 Feb; GHG accounting, crediting, FFI 5 Mar
• Discussed with Charl; next step: a first call with the macro unit
CDPM = the model formerly called SiSePuede. Sources: FY27 work plan v2.6; repos CPAT-AI, CPAT-CDPM, new-ai-tools; task tracker (20 Oct 2026)

## Slide 7: Products

## Slide 8: CPAT-AI (Excel-AI): mitigation MVP
 | Status and timeline
What it is | Cut-down CPAT in Excel, rebuilt with AI from legacy CPAT; every figure traceable to equation, parameter and source
Platform | Reference model for both platforms; feeds the WB-IMF CPAT process
Status (20 Oct) | v6.2 (20 Oct): mitigation, power and distribution built; legacy bugs fixed, not copied; MVP 70%
Next | Equations list, traceability, known-gaps note; Kacper holds the bug list while I travel
Timeline | MVP 23 Oct; power 2-13 Nov; remaining mitigation 16-27 Nov; final 4 Dec
Ask / risk | Ownership with the IMF/CPAT team; one Excel model, not two; data requests (GAINS, VAT)
CDPM = the model formerly called SiSePuede. Sources: FY27 work plan v2.6; repos CPAT-AI, CPAT-CDPM, new-ai-tools; task tracker (20 Oct 2026)

## Slide 9: Coded CPAT (Python)
 | Status and timeline
What it is | Python reimplementation of CPAT (mitigation + distribution), same codes as the Excel; Shiny app on top
Platform | The core of BOTH platforms: climate pathways and fiscal
Status (20 Oct) | Runs end to end; 57 tests; exports back to the legacy layout. Final Python 10%
Next | Port the validated Excel MVP logic; Python-vs-Excel comparison on the same inputs
Timeline | Enhanced version to Edmundo early Nov; final Python 11 Dec; Shiny app 5 Feb
Ask / risk | Open fixes: distribution revenue units, national totals, full electricity price build-up
CDPM = the model formerly called SiSePuede. Sources: FY27 work plan v2.6; repos CPAT-AI, CPAT-CDPM, new-ai-tools; task tracker (20 Oct 2026)

## Slide 10: Pathways: CPAT-CDPM integration (Edmundo)
 | Status and timeline
What it is | Coded CPAT inside CDPM (formerly SiSePuede; Edmundo Molina, Tec de Monterrey; with Dave Groves and Sonya Sampson): one pathways tool
Platform | Climate platform (pathways project)
Status (20 Oct) | Edmundo meeting 19 Oct went well: on track. CPAT sent; CPAT-CDPM repo created. Egypt proof of concept close to CPAT (-7.3% vs -8.0% emissions)
Next | Integrate early (no wait for a final product); one user flow; methodology note on subsidies vs public investment
Timeline | User-flow workshop early Nov; integration 4-8 Jan; pilots (Libya, Egypt, Morocco) 11-15 Jan; end Jan
Ask / risk | Agree the methodology split (running subsidies vs upfront public investment) before integration
CDPM = the model formerly called SiSePuede. Sources: FY27 work plan v2.6; repos CPAT-AI, CPAT-CDPM, new-ai-tools; task tracker (20 Oct 2026)

## Slide 11: FTT national (Zoe)
 | Status and timeline
What it is | National-level data so FTT technology diffusion (power, cars, freight, heat, steel) runs on CPAT's countries
Platform | Climate platform; with MFMod, the bridge to the fiscal platform
Status (20 Oct) | Zoe delivering; I review. Progress % not yet reported
Next | Ask Zoe for a review date; then FTT + MFMod on one Python platform
Timeline | FTT project 27 Nov; FTT + MFMod working 12 Feb
Ask / risk | Decision: MFMod in or out for Feb (FTT-only is doable in the week)
CDPM = the model formerly called SiSePuede. Sources: FY27 work plan v2.6; repos CPAT-AI, CPAT-CDPM, new-ai-tools; task tracker (20 Oct 2026)

## Slide 12: Investment needs (NMIM)
 | Status and timeline
What it is | National mitigation investment model: 186 countries, 2024-2050, built to CPAT norms; who pays (public, utility, private)
Platform | Both: investment for pathways; budget need for the fiscal platform
Status (20 Oct) | v0.2 (20 Oct). 2030: about USD 5.1tn total, 1.7tn incremental; direct budget need ~14% (85% in low-income countries)
Next | Financing and debt layer linked to MFMod; load cost-of-capital data; add a price response
Timeline | Proposal stage: fits the pathways timeline (Jan) and the fiscal platform (Feb)
Ask / risk | The natural hook for the macro unit: investment -> debt and fiscal space in MFMod
CDPM = the model formerly called SiSePuede. Sources: FY27 work plan v2.6; repos CPAT-AI, CPAT-CDPM, new-ai-tools; task tracker (20 Oct 2026)

## Slide 13: CBAM policy tool
 | Status and timeline
What it is | Excel tool: what a domestic carbon price does to heavy industry and the EU CBAM charge; 6 policy scenarios
Platform | Fiscal platform (revenue, credits); process emissions feed the investment model
Status (20 Oct) | Egypt v3.0 (7 CBAM goods) and a global MVP v1.0 (9 Oct)
Next | CBAM modelling inside CPAT (to discuss); port to Python with coded CPAT
Timeline | To agree: after the Excel-AI final (4 Dec)
Ask / risk | No trade model; elasticities by judgement. Ask: is CBAM in CPAT a priority?
CDPM = the model formerly called SiSePuede. Sources: FY27 work plan v2.6; repos CPAT-AI, CPAT-CDPM, new-ai-tools; task tracker (20 Oct 2026)

## Slide 14: Excise Diagnostic and Tax & Macro-Fiscal Dashboard
 | Status and timeline
What it is | Excise Diagnostic (Sierra Leone, Uganda, Liberia) and a dashboard: 53 indicators, 217 countries
Platform | Fiscal platform: tax and macro-fiscal data layer
Status (20 Oct) | Done: both handed to Dirk early (week of 5 Oct); all 4 Objective 3 milestones complete
Next | Owners use them; one week of follow-up support
Timeline | Support 8-12 Mar 2027
Ask / risk | Owners not yet named; tools not validated
CDPM = the model formerly called SiSePuede. Sources: FY27 work plan v2.6; repos CPAT-AI, CPAT-CDPM, new-ai-tools; task tracker (20 Oct 2026)

## Slide 15: Timeline: FY27 milestones
Date | Milestone | Platform
19 Oct | Edmundo on track (done) | Climate
23 Oct | Excel-AI mitigation MVP | Both (reference)
27 Nov | Zoe's FTT national project | Climate
4 Dec | Final Excel-AI | Both (reference)
11 Dec | Final coded CPAT (Python) | Both
15 Jan | Pathways tool: integration and pilots | Climate
5 Feb | Shiny app over coded CPAT | Both
12 Feb | FTT + MFMod working | Fiscal (macro)
5 Mar | GHG accounting, crediting, FFI | Fiscal
20 Mar | Handover; contract ends | -
FY27 work plan v2.6 (15 Oct); away 21 Oct to about 2 Nov
Notes: Slack is about 3 days before 4 Dec; power was built early, which covers the trip.

## Slide 16: Looking ahead: topics to agree
• Expenditure policy: PFRs lack an expenditure-policy chapter; the platforms can supply one
• Energy fiscal risks: what the finance ministry carries (subsidies, utilities, fuel revenue); scope to agree
• Investment process: who pays (public, utility, private) and the budget need, from NMIM
• Macro unit: shared Python code base; MFMod for debt and growth
CDPM = the model formerly called SiSePuede. Sources: FY27 work plan v2.6; repos CPAT-AI, CPAT-CDPM, new-ai-tools; task tracker (20 Oct 2026)

## Slide 17: Asks for today
• Agree the two platforms, with coded CPAT in both
• An introduction to the macro unit (MFMod-Python) for a first call in November
• Steer on the look-ahead: expenditure policy, energy fiscal risks, the investment process
• Decide: MFMod in or out for the February FTT milestone
• Resources: Claude Code ($200); widening the prototype team
• CBAM in CPAT: priority or not?
CDPM = the model formerly called SiSePuede. Sources: FY27 work plan v2.6; repos CPAT-AI, CPAT-CDPM, new-ai-tools; task tracker (20 Oct 2026)

## Slide 18: Thank you
Away 21 Oct to about 2 Nov; Kacper covers CPAT
Stephen Stretton